## Cover Page
Scope of Work | Project type (SFD, Duplex, etc. | Single-family house
for | Address | 2903
|  | Road Runner | 2903 Road Runner
Road Runner-2017 |  | College Town
River
expected to start on or about |  | Texas
77802
2017-05-04
and run through
2017-09-21

## Project Summary
Project Summary
This project (Road Runner-2017) consists of redeveloping a Single-family house described as follows:
2903 Road Runner
College Town, River, Texas 77802
3274 | square feet
Contractors selected to implement this project must have the following qualities:
➢ Saftey
➢ Speed with efficiency
➢ Cleanliness of job site
➢ A professional, well-finished product
All contractors and subcontractors on this project must be fully licensed, bonded, and insured.
Hermit Haus Redevelopment, LLC does not directly pick up, deliver, install, any materials. Any reference in this document to Hermit Haus Redevelopment, LLC providing and/or installing a fixture, finish, or material means that either the vendor or the contractor is responsible for the delivery of that material or coordination of the installation.
Before inspection of the property for the final punch list, the house must be prepped with a thorough cleaning of all windows and floors to the satisfaction of Hermit Haus Redevelopment, LLC.
The project is to be completed from the outside in. Quotes must include all labor and materials, including hauling and removal of unwanted and unused construction debris. Please email your quotes to info@hermithaus.com
Bids must be submitted using this document. Hermit Haus Redevelopment will not honor any other document. Any changes to this document must be agreed to by both the contractor and Hermit Hause management.
Contractor Signature:
Contractor Name:
Hermit Haus Redevelopment, LLC:
Date:
Tracking Data
| Element | Planned | Actual | Variance | Variance % | x/sf | Variance/Sf
| Purchased | 2017-05-01 | 2017-05-01 | 0 | 0%
| Start Date | 2017-05-04 | 2017-07-01 | 58 | 0.1353%
| End Date | 2017-09-21 | 2017-09-21 | 0 | 0%
| Duration | 140 | 82 | -58 | -41.43% | 0.025046 | -1.772%
| Budget | 68313.5355 | 40 | -68273.5355 | -99.94% | 0.012217 | -20.8532
| Staged | 2017-09-21 | 2017-09-22 | 1 | 0.002326%
| Listed | 2017-09-22 | 2017-09-23 | 1 | 0.002326%
| First Contract | 2017-10-13 | 2017-10-14 | 1 | 0.002324%
| Sale Closed | 2017-11-28 | 2017-11-28 | 0 | 0%
| Held | 211 | 211 | 0 | 0% | 0.064447 | 0%
| Purchase $ | 185000 | 121500 | -63500 | -34.32% | 37.1106 | -19.3952
| Sale $ | 280000 | 280000 | 0 | 0% | 85.5223 | 0
| Gross Profit | 26686.4645 | 158460 | 131773.5355 | 493.8% | 48.3995 | 40.2485
| Commissions | 16800 | 16800 | 0 | 0% | 5.1313 | 0
| Carrying Costs | 14846.9878 | 7123.5944 | -7723.3933 | -52.02% | 2.1758 | -2.359
| Closing Costs | 8400 | 8400 | 0 | 0% | 2.5657 | 0
| NOI | -13360.5233 | 126136.4056 | 139496.9288 | -1044% | 38.5267 | 42.6075
Formulas:
Actual = [Planned]
Actual = [Planned]+1
Planned = [Actual, row above]
Planned = [Planned, row above]+21

## Exterior Demo
Exterior Demo and General Work
Project: | Road Runner-2017
Contractor:
Remove all trash from front and back yards. Remove dead trees. Other demo work to be done.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Trash Disposal | TBD | Trash removal and dump fees for exterior demo. | 2017-05-09 | 2017-05-16 |  |  | 10
|  | Trash removal and dump fees for interor demo. | 2017-05-23 | 2017-05-30 |  |  | 10
|  | Other trash removal and dump fees. | 2017-09-14 | 2017-09-21 |  |  | 10
|  | Total Dumpster |  |  |  |  | 30 | 0
Yard | Cameron Lawn Maintenance | Lawn mowing and maintenance 1 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-24 | 40 | 40
|  | Lawn mowing and maintenance 2 | 2017-07-13 |  |  |  | 40
|  | Lawn mowing and maintenance 3 | 2017-08-03 |  |  |  | 40
|  | Lawn mowing and maintenance 4 | 2017-08-24 |  |  |  | 0
|  | Clean mow and weed flower beds prior to marketing. | 2017-09-14 |  |  |  | 40
| TBD | Fill in low spot in front yard and plant shrubs | 2017-08-03 |  |  |  | 100
Front porch | TBD | Demo front entry arches and dispose of debris |  |  |  |  | 850
Other | Contingency | Other external demolition |  |  |  |  | 58.5
Changes | TBD | Exterior Change order 1 |  |  |  |  | 0
| TBD | Exterior Change order 2 |  |  |  |  | 1
| TBD | Exterior Change order 3
Formulas:
Start Date = [Scheduled Complete, row above]+7
Start Date = [Scheduled Complete]-7
Scheduled Complete = [Start Date]+7

## Roof and Attic
Roof and Attic
Project: | Road Runner-2017
Contractor: | N/A
No roof work is anticipated for this project.
Repair roof and reseal vent pipes and other roof piercings as needed.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Roof | Roofer | No roof work is anticipated for this project. | 2017-05-04 | 2017-05-06
Match shingles to existing roof.
Repair decking as needed.
Reseal all vent pipes and other protrusions through the roof.
Paint pipes and vents to match roof.
Roof | Roofer | Remove and replace roof. | 2017-05-04 | 2017-05-07
High-quality x color shingles.
Galvanized metal valleys, etc.
Ridge vents
Seal all vent pipes and other protrusions through the roof.
Paint pipes and vents to match roof.
Attic | Out for Bid | Miscellaneous attic work
Replace insulation as needed.
Remove rodent nests and repair access.
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Scheduled Complete = [Start Date]+2

## Building Exterior
Building Exterior
Project: | Road Runner-2017
Contractor:
Repair facia, soffit and trim. Repair building siding and brickwork. Replace entry and exit doors and windows. Replace exterior lighting.
Add or repair gutters.
Add or repair purgola and decking.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Facia, soffit, and trim | None anticipated. | Repair all damaged facia, soffit, and trim, including trim around windows. |  |  |  |  | 0
0 lf of facia
0 lf of soffit
0 lf of trim
Siding | Scoped with windows | Replace damaged siding and install 1x4" trim along bottom |  |  |  |  | 0
Siding is in good condition, but some will need to be added as part of the window work described below.
Gutters | None scoped. | Replace or install extruded gutters and downspouts. | 1899-12-31 | 1899-12-31 |  |  | 0
Gutters must be extruded on site, not pieced together.
Drains must carry water at least four feet from building.
Paint | Out for Bid | Powerwash and paint all exterior surfaces. | 1900-01-01 | 1900-01-03 |  |  | 2650
Facia paint color: Burning Bush PPG 1057-7
Soffit paint color: Burning Bush PPG 1057-7
Trim paint color: Burning Bush PPG 1057-7
Window trim paint color: Burning Bush PPG 1057-7
Brick paint color: Rosey PPG 1061-4
Siding paint color: Irish Cream PPG 1061-1
Other paint color: NA
Deck | None scoped | Repair or add deck to back of the house |  |  |  |  | 0
Deck design per attached document
Deck stain code:
Pergola | None scope | Repair or add Pergola to back of the house |  |  |  |  | 0
Pergola design per attached document
Pergola stain code:
Windows | Out for Bid | Replace exterior windows.
Use high-quality double paned windows
Six lites plus arch where needed
|  | Front Office windows, 40 x 50 - 1, 20 x 60 - 2. Raise frame, install siding, trim. Shingle to match roof. |  |  |  |  | 1550
|  | Family Room windows - Retrofits 30 x 60 |  |  |  |  | 1650
|  | Upstairs front windows - Arch 20 x 40 -6 qty |  |  |  |  | 3140
|  | Upstairs Bedroom windows - 2 qty 30 x 60 |  |  |  |  | 590
|  | Upstairs M. Bedroom windows - 2 qty 40 x 60 |  |  |  |  | 920
Window 6
French doors | Out for Bid | Replace sliding glass door in dining room with French doors. |  |  |  |  | 1150
Contingency | [6 empty] | 582.5
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Scheduled Complete = [Start Date]
Scheduled Complete = [Start Date]+2

## Landscaping
Landscaping
Project: | Road Runner-2017
Contractor: | Landscaper
Reseed or resod front and back yards
Plant shrubs and flowers.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Lawn | Out for Bid | Reseed or resod front and back lawns. |  |  |  |  | 200
Type of grass
Shrubs and trees | Out for Bid | Plant shrubs and trees in front and back yards |  |  |  |  | 200 | 0
|  | 5 drought-tollerant shrubs up to $15 ea |  |  |  |  | 75
|  | 2 trees up to $25 each |  |  |  |  | 75
Tree 1
Tree 2
Tree 3
|  | Labor |  |  |  |  | 50
Flower beds | Out for Bids | Plant flowers in beds in front and back of the house |  |  |  |  | 150 | 0
|  | Front Flower beds to $100 |  |  |  |  | 100
|  | Back Flower Beds to $50 |  |  |  |  | 50
Dtainage | Out for Bids | Cut driveway concrete for French drain |  |  |  |  | 1270
|  | Install Drain - Grates full length, PVC lines, and recover with appropriate materials |  |  |  |  | 2150
|  | Remove debris. |  |  |  |  | Included
Fencing | None scoped | Replace or repair fence around the back yard. |  |  |  |  | 0
6"x.5"x6' treated pine pickets, standard
4x4 treated pine posts
2x4 treated pine rails
Do not stain or paint
Contingency | [6 empty] | 216
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3

## Interior Demo
Interior Demolition
Project: | Road Runner-2017
Contractor: | Lead Contractor
Reseed or resod front and back yards
Plant shrubs and flowers.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Planned Demo | Out for Bids | Planned demolition |  |  |  |  | 3183.5 | 0
|  | Remove all trash from interior of the house |  |  |  |  | 0
|  | Wall opening to dining, remove cabinets and wall |  |  |  |  | 870
|  | Remove all kitchen appliances |  |  |  |  | 0
|  | Remove all flooring, including carpets, carpet stretchers, tile, and laminates. |  |  |  |  | 1438.5
|  | Remove furdowns in hall bath |  |  |  |  | 350
|  | Demo and support beam entering family room |  |  |  |  | 425
|  | Final cleanup |  |  |  |  | 100
Ceilings | Out for Bids | Remove all popcorn from ceilings
Contingency | [6 empty] | 318.35
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3

## Plumbing
General Plumbing
Project: | Road Runner-2017
Contractor: | Plumber | License #
Bring all plumbing to current code. Pull permits as needed.
See Kitchen and Bathrooms for additional work.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Permits | Out for Bids | Pull permits as needed to complete work described below. | 2017-05-04 | 2017-05-19 |  |  | 300
Water heater | Out for Bids | Raise water heater in laundry area and bring to current code. | 2017-05-19 | 2017-05-20 |  |  | 795 | 0
|  | Water heater and installation supplies. |  |  |  |  | 795
|  | Bring to current code. |  |  |  |  | 0
|  | Where needed, replace water lines with PEX |  |  |  |  | 0
Exterior | Not scoped | Replace all exterior faucets. | 2017-05-04 | 2017-05-04 12:00 |  |  | 0 | 0
|  | x number of faucets. |  |  |  |  | 0
|  | Standard or Quarter Turn faucets |  |  |  |  | 0
Misc. | Out for bids | Miscellaneous work immediately following demolition. | 2017-05-20 | 2017-05-25 |  |  | 275 | 0
|  | Install new angle stops on all water lines. |  |  |  |  | 25
|  | Install Pro-Flex gas lines at all gas feed equipment (water heater, range, furnace, etc.). |  |  |  |  | 0
|  | Check all drain lines and vents. Repair or replace as needed. |  |  |  |  | 100
|  | Install water line for refrigerator (regardless of fridge type). |  |  |  |  | 50
|  | Ensure there is a pressure regulator or install one if there isn't one and make sure the water pressure is between 60-90 PSI. |  |  |  |  | 100
Kitchen and Baths | Out for Bids | See kitchen and bathroom pages for a description of all work to be done. |  |  |  |  | 0 | 0
Contingency | [6 empty] | 122
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Scheduled Complete = [Start Date]+15
Scheduled Complete = [Start Date]+0.5

## Electrical
Electrical
Project: | Road Runner-2017
Contractor: | Electrician | License #
Bring all electrical to current code. Pull permits as needed.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Permits | Out for Bids | Pull permits as needed to complete work described below. | 2017-05-04 | 2017-05-19 |  |  | 300
Service Connect | Not scoped | Bring electrical service connect to code. | 2017-05-19 | 2017-05-21 |  |  | 0 | 0
|  | Full service weatherhead, riser, feeder, meter socket, panel, breakers, grounding, and permits |  |  |  |  | 0
Pull new circuits as required.
Kitchen and Baths |  | See the sections on kitchen and bathrooms for additional information. | 2017-05-19 | 2017-05-20 |  |  | 0 | 0
Misc. Electrical | Out for bids | Fix various code and esthetic issues, including all listed in Inspection Report. | 2017-05-22 | 2017-05-24 |  |  | 2027.5 | 0
|  | Replace all swtiches and outlets with white decore electrical outlets and switches and ensure proper grounding |  |  |  |  | 550
|  | Install USB power outlets in the kitchen, dining area, and each bedroom |  |  |  |  | 280
|  | Replace all GFCI outlets |  |  |  |  | 860
|  | Install water heater, dryer, and dishwasher plugs - in wall |  |  |  |  | 337.5
|  | Repair any open junction points in attic, garage, walls, or crawlspaces. |  |  |  |  | 0
Fixtures | Out for Bids | Replace all light fixtures | 2017-05-24 | 2017-05-25 |  |  | 2830
|  | Chandelier in dining area |  |  |  |  | 350
|  | Can LED, Office - 6, Kit - 6, Laud - 2, Halls - 2 |  |  |  |  | 1700
|  | Recessed lighting in all bedrooms |  |  |  |  | 0
|  | Install mushroom lights in hall/closets (12 qty) |  |  |  |  | 780
Exterior | Out for Bids | Replace all exterior lights. (7 @ $60 allowance) | 2017-05-25 | 2017-05-25 |  |  | 700
Description of fixtures
Ceiling Fans | Out for Bids | Replace ceiling fans (allow $800 for materials) | 2017-05-26 | 2017-05-27 |  |  | 1400
Living room
Master bedroom
Guest bedroom 1
Guest bedroom 2
Smoke & CO2 | Out for Bids | Install smoke detectors and CO2 detectors as required by code. | 2017-05-27 | 2017-05-28
Contingency | [6 empty] | 605.75
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Scheduled Complete = [Start Date]+15
Scheduled Complete = [Start Date]

## HVAC
HVAC
Project: | Road Runner-2017
Contractor: | HVAC | License #
Inspect current HVAC system and service if warranted. If additional trips are required to service or replace the HVAC system, cost of the initial trip will be rolled into the subsequent bid.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Test and Service | Out for bid | Test and service existing HVAC. Make recommendations for repair/replacement with justification. Cost will be applied to further work, if approved. | 2017-05-04 | 2017-05-09 |  |  | 200
Permits | Not in scope | Pull permits as needed to complete work described below. | 2017-05-14 | 2017-05-29 |  |  | 500
Duct work | Not in scope | Demo any existing ductwork and replace to current code. | 2017-05-14 | 2017-05-16
Mechanicals | Not in scope | Replace existing mechanicals with high-efficiency equipment and programable thermostats | 2017-05-30 | 2017-06-04
Inside forced air unit 1
Outside Compressor 1
Inside forced air unit 2
Outside Compressor 2
Contingency | [6 empty] | 35
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Scheduled Complete = [Start Date]+5
Scheduled Complete = [Start Date]+COUNTA([License #, row below]:C23)

## Walls & Ceilings
Walls and Ceilings
Project: | Road Runner-2017
Contractor: | TBD | License #
Replace any damaged drywall and install drywall in new construction areas as needed.
Tape and float all installation and repairs.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Dry wall | Out for Bid | Install or repair and tape/float drywall in the following areas | 0 | 1900-01-07 |  |  | 1675
|  | Kitchen - opening to dining room | 0.5 | 0.5 |  |  | 575
|  | Living Room | 1899-12-31 | 1899-12-31
|  | Laundry Room | 1899-12-31 12:00 | 1899-12-31 12:00
|  | Dining Room | 1900-01-01 | 1900-01-01
|  | Second Living Room | 1900-01-01 12:00 | 1900-01-01 12:00
|  | Master Suite | 1900-01-02 | 1900-01-02
|  | Guest Bath 1, including hardie | 1900-01-02 12:00 | 1900-01-02 12:00
|  | Guest Bath 2, including hardie | 1900-01-03 | 1900-01-03
|  | Guest Bath 3, including hardie | 1900-01-03 12:00 | 1900-01-03 12:00
|  | Guest Bath 4, including hardie | 1900-01-04 | 1900-01-04
|  | Bedroom 2 | 1900-01-04 12:00 | 1900-01-04 12:00
|  | Bedroom 3 | 1900-01-05 | 1900-01-05
|  | Bedroom 4 | 1900-01-05 12:00 | 1900-01-05 12:00
|  | Bedroom 5 | 1900-01-06 | 1900-01-06
|  | All lighting repairs | 1900-01-06 12:00 | 1900-01-06 12:00 |  |  | 1100
|  | Bonus Room | 1900-01-07 | 1900-01-07
Trim | Out for Bid | Install Shoe and Crowne moldings (Living room and Master only) | 1900-01-08 | 1900-01-19 06:00 |  |  | 550
|  | Kitchen | 1900-01-08 18:00 | 1900-01-08 18:00
|  | Living Room | 1900-01-09 12:00 | 1900-01-09 12:00
|  | Laundry Room | 1900-01-10 06:00 | 1900-01-10 06:00
|  | Dining Room | 1900-01-11 | 1900-01-11
|  | Second Living Room | 1900-01-11 18:00 | 1900-01-11 18:00
|  | Master Suite | 1900-01-12 12:00 | 1900-01-12 12:00
|  | Guest Bath 1 | 1900-01-13 06:00 | 1900-01-13 06:00
|  | Guest Bath 2 | 1900-01-14 | 1900-01-14
|  | Guest Bath 3 | 1900-01-14 18:00 | 1900-01-14 18:00
|  | Guest Bath 4 | 1900-01-15 12:00 | 1900-01-15 12:00
|  | Bedroom 2 | 1900-01-16 06:00 | 1900-01-16 06:00
|  | Bedroom 3 | 1900-01-17 | 1900-01-17
|  | Bedroom 4 | 1900-01-17 18:00 | 1900-01-17 18:00
|  | Bedroom 5 | 1900-01-18 12:00 | 1900-01-18 12:00
|  | Replacve door to storage area under stairs |  |  |  |  | 550
|  | Bonus Room | 1900-01-19 06:00 | 1900-01-19 06:00
Repair Beam |  | Install new LVL beam entering family room & drywall |  |  |  |  | 1550
Contingency | [6 empty] | 300
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Start Date = [Start Date, row above]+0.5
Scheduled Complete = MAX([Scheduled Complete, row below]:E28)
Scheduled Complete = [Start Date]

## Paint
Paint
Project: | Road Runner-2017
Contractor: | TBD | License #
Paint interior and exterior of the house with the specified paint colors.
Leave excess paint in the appropriate room's closet
Final touchup near the end of the project
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Interior | Out for Bid | Paint each room the color(s) specified for wall/trim/ accent. Paint ceilings white unless otherwise specified | 0 | 1900-01-06 12:00 |  |  | 5180
|  | Kitchen | 0.5 | 0.5
|  | Living Room | 1899-12-31 | 1899-12-31 |  |  | 1320
|  | Laundry Room | 1899-12-31 12:00 | 1899-12-31 12:00 |  |  | 2800
|  | Dining Room | 1900-01-01 | 1900-01-01
|  | Second Living Room | 1900-01-01 12:00 | 1900-01-01 12:00
|  | Master Suite | 1900-01-02 | 1900-01-02
|  | Guest Bath 1 | 1900-01-02 12:00 | 1900-01-02 12:00
|  | Guest Bath 2 | 1900-01-03 | 1900-01-03
|  | Guest Bath 3 | 1900-01-03 12:00 | 1900-01-03 12:00
|  | Guest Bath 4 | 1900-01-04 | 1900-01-04
|  | Bedroom 2 | 1900-01-04 12:00 | 1900-01-04 12:00
|  | Bedroom 3 | 1900-01-05 | 1900-01-05
|  | Bedroom 4 | 1900-01-05 12:00 | 1900-01-05 12:00
|  | Bedroom 5 | 1900-01-06 | 1900-01-06
|  | Doors/Trim |  |  |  |  | 1060
|  | Bonus Room | 1900-01-06 12:00 | 1900-01-06 12:00
Exterior | Out for Bid | See Building Exterior |  |  |  |  | 0
Touchup | Out for bid | Touch up all interior surfaces | 1900-01-07 12:00 | 1900-01-08 12:00 |  |  | 200
Contingency | [6 empty] | 528
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Start Date = [Start Date, row above]+0.5
Start Date = MAX(E12:[Scheduled Complete, row above])+1
Scheduled Complete = MAX([Scheduled Complete, row below]:E28)
Scheduled Complete = [Start Date]

## Flooring
Flooring
Project: | Road Runner-2017
Contractor: | TBD | License #
Install or repair flooring and do any repairs needed for proper installation.
Leave excess paint in the appropriate room's closet
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Interior | Out for Bid | Install or repair flooring in each room | 0 | 1900-01-06 12:00 |  |  | 12134.88
|  | Kitchen - tile | 0.5 | 0.5
|  | Family Room - Carpet | 1899-12-31 | 1899-12-31 |  |  | 5150.16
|  | Laundry Room - Tile | 1899-12-31 12:00 | 1899-12-31 12:00 |  |  | 5103.72
|  | Dining Room - Tile | 1900-01-01 | 1900-01-01 |  |  | 300
|  | Second Living Room - Tile | 1900-01-01 12:00 | 1900-01-01 12:00 |  |  | 1581
|  | Master Suite - Carpet/Tile | 1900-01-02 | 1900-01-02
|  | Guest Bath 1 - Tile | 1900-01-02 12:00 | 1900-01-02 12:00
|  | Guest Bath 2 - Tile | 1900-01-03 | 1900-01-03
|  | Guest Bath 3 - Tile | 1900-01-03 12:00 | 1900-01-03 12:00
|  | Guest Bath 4 - Tile | 1900-01-04 | 1900-01-04
|  | Bedroom 2 - Carpet | 1900-01-04 12:00 | 1900-01-04 12:00
|  | Bedroom 3 - Carpet | 1900-01-05 | 1900-01-05
|  | Bedroom 4 - Carpet | 1900-01-05 12:00 | 1900-01-05 12:00
|  | Bedroom 5 - Carpet | 1900-01-06 | 1900-01-06
|  | Bonus Room - Carpet | 1900-01-06 12:00 | 1900-01-06 12:00
Contingency | [6 empty] | 1213.488
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Start Date = [Start Date, row above]+0.5
Scheduled Complete = MAX([Scheduled Complete, row below]:E27)
Scheduled Complete = [Start Date]

## Kitchen
Kitchen
Project: | Road Runner-2017
Contractor: | TBD | License #
Install kitchen cabinets, countertops, fixtures, lighting, and plumbing to current code.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Cabinets | Out for Bid | Paint kitchen cabinets and doors | 0 | 1900-01-05 |  |  | 2000
Color of uppers
Color of lowers
Backsplashes | Out for Bid | Install backsplashes with decorative element. | 0.5 | 0.5 |  |  | TBD
Countertops | Out for Bid | Install countertops | 0.5 | 0.5 |  |  | TBD
Sinks | Out for Bid | Install and test sinks, including faucets, water supply, drains, and garbage disposal. | 1899-12-31 | 1899-12-31 |  |  | 0
|  | Main sink | 1899-12-31 12:00 | 1899-12-31 12:00 |  |  | TBD
|  | Optional pot filler / sink | 1900-01-01 | 1900-01-01 |  |  | 0
Appliances | Out for Bid | Install and test all appliances. $3000 appliane allowance | 1900-01-01 12:00 | 1900-01-01 12:00 |  |  | 3700
|  | Dishwasher | 1900-01-02 | 1900-01-02 |  |  | 500
|  | Range | 1900-01-02 12:00 | 1900-01-02 12:00 |  |  | 800
|  | Oven(s) | 1900-01-03 | 1900-01-03 |  |  | 800
|  | Microwave | 1900-01-03 12:00 | 1900-01-03 12:00 |  |  | 0
|  | Vent Hood | 1900-01-04 | 1900-01-04 |  |  | 50
|  | Garbage Disposal | 1900-01-04 12:00 | 1900-01-04 12:00 |  |  | 150
|  | Refrigerator with ice maker | 1900-01-05 | 1900-01-05 |  |  | 700
Contingency | [6 empty] | 435
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Start Date = [Start Date, row above]+0.5
Scheduled Complete = [Start Date]

## Baths
Bathrooms
Project: | Road Runner-2017
Contractor: | TBD | License #
Install bathroom cabinets, countertops, fixtures, shower enclosures. lighting, and plumbing to current code.
Remove all debris and trash from site.
Materials will be included in bid and paid on completion.
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount
Master Bath |  | Make it nice. | 1899-12-31 | 1900-01-01 |  |  | 3457
|  | Install all cabinets and countertops as specified on the bathroom plan. |  |  |  |  | 475
|  | Create a custom shower enclosure with decorative accents. | 1900-01-01 | 1900-01-03 |  |  | 1290
|  | Install and test sink and faucets. | 1900-01-01 | 1900-01-02 |  |  | 0
|  | Install and test rain shower head and controls. | 1900-01-03 | 1900-01-03 12:00 |  |  | 0
|  | Install and test tub and faucets. | 1900-01-03 12:00 | 1900-01-04 |  |  | 0
|  | Install decorative mirror over sink. | 1900-01-04 | 1900-01-04 12:00 |  |  | TBD
|  | Install vanity lights and recessed light in shower and main ceiling. | 1900-01-04 12:00 | 1900-01-05 |  |  | 200
Hall Bath |  | Make it nice | 1900-01-01 | 1900-01-02 |  |  | 1492
|  | Install all cabinets and countertops as specified on the bathroom plan. |  |  |  |  | 425
|  | Create a nice shower enclosure with decorative accents. | 1900-01-02 | 1900-01-04 |  |  | 900
|  | Install and test sink and faucets. | 1900-01-02 | 1900-01-03 |  |  | 0
|  | Install and test rain shower head and controls. | 1900-01-04 | 1900-01-04 12:00 |  |  | 0
|  | Install and test tub and faucets. | 1900-01-04 12:00 | 1900-01-05 |  |  | 0
|  | Install decorative mirror over sink. | 1900-01-05 | 1900-01-05 12:00 |  |  | TBD
|  | Install vanity lights and recessed light in shower and main ceiling. | 1900-01-05 12:00 | 1900-01-06 |  |  | 167
Second Master |  | make it nice | 1900-01-02 | 1900-01-03 |  |  | 1677
|  | Install all cabinets and countertops as specified on the bathroom plan. |  |  |  |  | 475
|  | Create a nice shower enclosure with decorative accents. | 1900-01-03 | 1900-01-05 |  |  | 1035
|  | Install and test sink and faucets. | 1900-01-03 | 1900-01-04
|  | Install and test rain shower head and controls. | 1900-01-05 | 1900-01-05 12:00 |  |  | 0
|  | Install and test tub and faucets. | 1900-01-05 12:00 | 1900-01-06 |  |  | 0
|  | Install decorative mirror over sink. | 1900-01-06 | 1900-01-06 12:00 |  |  | TBD
|  | Install vanity lights and recessed light in shower and main ceiling. | 1900-01-06 12:00 | 1900-01-07 |  |  | 167
Laundry Bath |  | Make it nice | 0 | 1899-12-31 |  |  | 1292
|  | Install all cabinets and countertops as specified on the bathroom plan. |  |  |  |  | 225
|  | Create a nice shower enclosure with decorative accents. | 1899-12-31 | 1900-01-02 |  |  | 900
|  | Install and test sink and faucets. | 1899-12-31 | 1900-01-01 |  |  | 0
|  | Install and test rain shower head and controls. | 1900-01-02 | 1900-01-02 12:00 |  |  | 0
|  | Install and test tub and faucets. | 1900-01-02 12:00 | 1900-01-03 |  |  | 0
|  | Install decorative mirror over sink. | 1900-01-03 | 1900-01-03 12:00 |  |  | TBD
|  | Install vanity lights and recessed light in shower and main ceiling. | 1900-01-03 12:00 | 1900-01-04 |  |  | 167
Contingency | [6 empty] | 717.2
Changes | TBD | Change order 1
| TBD | Change order 2
| TBD | Change order 3
Formulas:
Start Date = [Scheduled Complete, row above]
Scheduled Complete = [Start Date]+1
Scheduled Complete = [Start Date]+0.5

## Payment Schedule
Payment Schedule
Exhibit B
All payments will be made on the Friday following completion of the work described herein. Completion occurs with the work is finished to code and accepted by Hermit Haus Redevelopment by Wednesday of the week to be paid. Date-based payments are expressly denied by accepting work from Hermit Haus Redevelopment.
Project: | Road Runner-2017
Phase | Contractor | Milestone/Benchmark | Start Date | Scheduled Complete | Actual Complete | Payment Date | Budgeted Amount | Payment Amount | Completion Variance | Completion Variance % | Budget Variance | Budget Variance %
Exterior Demo and General Work
Trash Disposal | TBD | Trash removal and dump fees for exterior demo. | 2017-05-09 | 2017-05-16 | 0 | 0 | 10 | 0 | - | 0% | -10 | 100%
|  | Trash removal and dump fees for interor demo. | 2017-05-23 | 2017-05-30 | 0 | 0 | 10 | 0 | - | 0% | -10 | 100%
|  | Other trash removal and dump fees. | 2017-06-10 | 2017-06-17 | 0 | 0 | 10 | 0 | - | 0% | -10 | 100%
Yard | Cameron Lawn Maintenance | Lawn mowing and maintenance 1 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-24 | 40 | 40 | 0 | 100% | 0 | 0%
|  | Lawn mowing and maintenance 2 | 2017-07-13 | 0 | 0 | 0 | 40 | 0 | - | 0% | -40 | 100%
|  | Lawn mowing and maintenance 3 | 2017-08-03 | 0 | 0 | 0 | 40 | 0 | - | 0% | -40 | 100%
|  | Lawn mowing and maintenance 4 | 2017-08-24 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
|  | Clean mow and weed flower beds prior to marketing. | 2017-09-14 | 0 | 0 | 0 | 40 | 0 | - | 0% | -40 | 100%
|  | Fill in low spot in front yard and plant shrubs | 2017-08-03 | 0 | 0 | 0 | 100 | 0 | - | 0% | -100 | 100%
Front porch | TBD | Demo front entry arches and dispose of debris | 0 | 0 | 0 | 0 | 850 | 0 | - | 0% | 0 | 100%
Other | Contingency | Other external demolition | 0 | 0 | 0 | 0 | 58.5 | 0 | - | 0% | 0 | 100%
Other | Contingency | Other external demolition | 0 | 0 | 0 | 0 | 58.5 | 0 | - | 0% | -58.5 | 100%
Changes | TBD | Exterior Change order 1 | 0 | 0 | 0 | 0 | 62.85 | 0 | - | 0% | -62.85 | 100%
| TBD | Exterior Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Exterior Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Roof and Attic
Roof | Roofer | No roof work is anticipated for this project. | 2017-05-04 | 2017-05-06 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Roof | Roofer | Remove and replace roof. | 2017-05-04 | 2017-05-07 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Attic | Out for Bid | Miscellaneous attic work | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
|  | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
|  | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Building Exterior
Facia, soffit, and trim | None anticipated. | Repair all damaged facia, soffit, and trim, including trim around windows. | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Siding | Scoped with windows | Replace damaged siding and install 1x4" trim along bottom | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Gutters | None scoped. | Replace or install extruded gutters and downspouts. | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Paint | Out for Bid | Powerwash and paint all exterior surfaces. | 1900-01-01 | 1900-01-03 | 0 | 0 | 2650 | 0 | - | 0% | -2650 | 100%
Deck | None scoped | Repair or add deck to back of the house | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Pergola | None scope | Repair or add Pergola to back of the house | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Windows | Out for Bid | Replace exterior windows. | 0 | 0 | 0 | 0 | 7850 | 0 | - | 0% | -7850 | 100%
French doors | Out for Bid | Replace sliding glass door in dining room with French doors. | 0 | 0 | 0 | 0 | 1150 | 0 | - | 0% | -1150 | 100%
Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 582.5 | 0 | - | 0% | -582.5 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 582.5 | 0 | - | 0% | -582.5 | 100%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Landscaping
Lawn | Out for Bid | Reseed or resod front and back lawns. | 0 | 0 | 0 | 0 | 200 | 0 | - | 0% | -200 | 100%
Shrubs and trees | Out for Bid | Plant shrubs and trees in front and back yards | 0 | 0 | 0 | 0 | 200 | 0 | - | 0% | -200 | 100%
Flower beds | Out for Bids | Plant flowers in beds in front and back of the house | 0 | 0 | 0 | 0 | 150 | 0 | - | 0% | -150 | 100%
Dtainage | Out for Bids | Cut driveway concrete for French drain | 0 | 0 | 0 | 0 | 1270 | 0 | - | 0% | -1270 | 100%
Fencing | None scoped | Replace or repair fence around the back yard. | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | - | 0% | -216 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 91 | 0 | - | 0% | -91 | 100%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Interior Demo
Planned Demo | Out for Bids | Planned demolition | 0 | 0 | 0 | 0 | 3183.5 | 0 | - | 0% | -3183.5 | 100%
Ceilings | Out for Bids | Remove all popcorn from ceilings | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Contingency |  |  | 0 | 0 | 0 | 0 | 318.35 | 0 | - | 0% | -318.35 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 175.0925 | 0 | - | 0% | -175.0925 | 100%
|  | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
|  | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
General Plumbing
Permits | Out for Bids | Pull permits as needed to complete work described below. | 2017-05-04 | 2017-05-19 | 0 | 0 | 300 | 0 | - | 0% | -300 | 100%
Water heater | Out for Bids | Raise water heater in laundry area and bring to current code. | 2017-05-19 | 2017-05-20 | 0 | 0 | 795 | 0 | - | 0% | -795 | 100%
Exterior | Not scoped | Replace all exterior faucets. | 2017-05-04 | 2017-05-04 12:00 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Misc. | Out for bids | Miscellaneous work immediately following demolition. | 2017-05-20 | 2017-05-25 | 0 | 0 | 275 | 0 | - | 0% | -275 | 100%
Kitchen and Baths | Out for Bids | Kitchen and bathroom plumbing to be paid under those line items. | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Contingency |  |  | 0 | 0 | 0 | 0 | 122 | 0 | - | 0% | -122 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 1370.05 | 0 | - | 0% | -1370.05 | 100%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Electrical
Permits | Out for Bids | Pull permits as needed to complete work described below. | 2017-05-04 | 2017-05-19 | 0 | 0 | 300 | 0 | -42874 | 0% | -300 | 100%
Service Connect | Not scoped | Bring electrical service connect to code. | 2017-05-19 | 2017-05-21 | 0 | 0 | 0 | 0 | -42876 | 0% | 0 | #DIV/0!
Kitchen and Baths | 0 | See the sections on kitchen and bathrooms for additional information. | 2017-05-19 | 2017-05-20 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Misc. Electrical | Out for bids | Fix various code and esthetic issues, including all listed in Inspection Report. | 2017-05-22 | 2017-05-24 | 0 | 0 | 2027.5 | 0 | - | 0% | -2027.5 | 100%
Fixtures | Out for Bids | Replace all light fixtures | 2017-05-24 | 2017-05-25 | 0 | 0 | 2830 | 0 | - | 0% | -2830 | 100%
Exterior | Out for Bids | Replace all exterior lights. (7 @ $60 allowance) | 2017-05-25 | 2017-05-25 | 0 | 0 | 700 | 0 | - | 0% | -700 | 100%
Ceiling Fans | Out for Bids | Replace ceiling fans (allow $800 for materials) | 2017-05-26 | 2017-05-27 | 0 | 0 | 1400 | 0 | - | 0% | -1400 | 100%
Smoke & CO2 | Out for Bids | Install smoke detectors and CO2 detectors as required by code. | 2017-05-27 | 2017-05-28 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Contingency |  |  | 0 | 0 | 0 | 0 | 605.75 | 0 | - | 0% | -605.75 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 362.875 | 0 | - | 0% | -362.875 | 100%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
HVAC
Test and Service | Out for bid | Test and service existing HVAC. Make recommendations for repair/replacement with justification. Cost will be applied to further work, if approved. | 2017-05-04 | 2017-05-09 | 0 | 0 | 200 | 0 | - | 0% | -200 | 100%
Permits | Not in scope | Pull permits as needed to complete work described below. | 2017-05-14 | 2017-05-29 | 0 | 0 | 500 | 0 | - | 0% | -500 | 100%
Duct work | Not in scope | Demo any existing ductwork and replace to current code. | 2017-05-14 | 2017-05-16 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Mechanicals | Not in scope | Replace existing mechanicals with high-efficiency equipment and programable thermostats | 2017-05-30 | 2017-06-04 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Contingency |  |  | 0 | 0 | 0 | 0 | 35 | 0 | - | 0% | -35 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Walls and Cilings
Dry wall | Out for Bid | Install or repair and tape/float drywall in the following areas | 0 | 1900-01-07 | 0 | 0 | 1675 | 0 | - | 0% | -1675 | 100%
Trim | Out for Bid | Install Shoe and Crowne moldings (Living room and Master only) | 1900-01-08 | 1900-01-19 06:00 | 0 | 0 | 550 | 0 | - | 0% | -550 | 100%
|  | Bedroom 5 | 1900-01-18 12:00 | 1900-01-18 12:00 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Contingency |  |  | 0 | 0 | 0 | 0 | 300 | 0 | - | 0% | -300 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Paint
Interior | Out for Bid | Paint each room the color(s) specified for wall/trim/ accent. Paint ceilings white unless otherwise specified | 0 | 1900-01-06 12:00 | 0 | 0 | 5180 | 0 | - | 0% | -5180 | 100%
Exterior | Out for Bid | See Building Exterior | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Touchup | Out for bid | Touch up all interior surfaces |  |  | 0 | 0 | 200 | 0 | - | 0% | -200 | 100%
Contingency |  |  | 0 | 0 | 0 | 0 | 528 | 0 | - | 0% | -528 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Flooring
Interior | Out for Bid | Install or repair flooring in each room | 0 | 1900-01-06 12:00 | 0 | 0 | 12134.88 | 0 | - | 0% | -12134.88 | 100%
Contingency |  |  | 0 | 0 | 0 | 0 | 1213.488 | 0 | - | 0% | -1213.488 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Kitchen
Cabinets | Out for Bid | Paint kitchen cabinets and doors | 0 | 1900-01-05 | 0 | 0 | 2000 | 0 | - | 0% | -2000 | 100%
Backsplashes | Out for Bid | Install backsplashes with decorative element. | 0.5 | 0.5 | 0 | 0 | TBD | 0 | - | 0% | 0 | 0%
Countertops | Out for Bid | Install countertops | 0.5 | 0.5 | 0 | 0 | TBD | 0 | - | 0% | 0 | 0%
Sinks | Out for Bid | Install and test sinks, including faucets, water supply, drains, and garbage disposal. | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Appliances | Out for Bid | Install and test all appliances. $3000 appliane allowance | 1900-01-01 12:00 | 1900-01-01 12:00 | 0 | 0 | 3700 | 0 | - | 0% | -3700 | 100%
Contingency |  |  | 0 | 0 | 0 | 0 | 435 | 0 | - | 0% | -435 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
| TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Bathrooms
Master Bath | 0 | Make it nice. | 1899-12-31 | 1900-01-01 | 0 | 0 | 3457 | 0 | - | 0% | -3457 | 100%
Hall Bath | 0 | Make it nice | 1900-01-01 | 1900-01-02 | 0 | 0 | 1492 | 0 | - | 0% | -1492 | 100%
Second Master | 0 | make it nice | 1900-01-02 | 1900-01-03 | 0 | 0 | 1677 | 0 | - | 0% | -1677 | 100%
Laundry Bath | 0 | Make it nice | 0 | 1899-12-31 | 0 | 0 | 1292 | 0 | - | 0% | -1292 | 100%
Contingency | 0 |  | 0 | 0 | 0 | 0 | 717.2 | 0 | - | 0% | -717.2 | 100%
Changes | TBD | Change order 1 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
0 | TBD | Change order 2 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
0 | TBD | Change order 3 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0 | 0%
Formulas:
Start Date = [Scheduled Complete]-7